## Slide 1: The Production & Rehearsal Processes

## Slide 2: Pre-production
Step 1: Choosing the show
Who’s involved?
Producer & investors
Director (maybe)
Considerations?
Finances & talent
Audience taste
Technical capabilities

## Slide 3: Pre-production
Step 2: Hiring the talent
The Director analyzes the script (2-3 readings) and comes up with a “vision” for the production as a whole… what he/she wants the audience to take away with them from seeing the show
Then, techs and actors are hired to bring that “vision” to life

## Slide 4: Pre-production
Step 2: Hiring the talent (actors)
Types of Auditions:
Open audition – for any interested actor
Closed audition – only for certain groups/students
Prepared audition – actor prepares his/her choice of material
Cold reading – actor auditions with material provided at the audition, little prep time
Improvisational – actor provided with character/situation and must improvise around it

## Slide 5: Pre-production
Audition Prep for the actor
How to prepare:
Know the play & character you’re auditioning for
Prepare the correct audition material
Complete the audition form or bring a resume is needed
Arrive early for the audition, dress professionally
Remember: the audition begins the moment they see you, not just when they say “go”

## Slide 6: Production
Beginning the production process
Work is divided into tech & actor categories
Both groups work parallel to each other with some overlap when needed
Director & Stage Manager work with both groups
Producer & Business Manager supervise ($$)

## Slide 7: Production
Step 1: Table Read
WHO:
all actors, Director, SM, TM, needed Crew
WHAT:
Read through entire play for familiarity

## Slide 8: Production
Step 2: Blocking Rehearsals
(on-book)
WHO:
Actors, Director, SM, needed Designers
WHAT:
Director gives actors their movement, actors & SM record EVERYTHING!!

## Slide 9: Production
Step 3: Working Rehearsals
(off-book)
WHO:
Actors, Director, SM
WHAT:
work on characterization, perfect movement & scene development

## Slide 10: Production
Step 4: Polishing Rehearsals
(off-book)
WHO:
Actors, Director, SM, TM, Designers
WHAT:
clean up & perfect scenes, adjust acting/designs to work together, final fixes

## Slide 11: Production
Step 5: Dress Rehearsal
(off-book)
WHO:
Actors, Director, SM, TM, Costumes, Lights
WHAT:
run show start to finish in full costumes to look for problems & fixes

## Slide 12: Production
Step 6: Tech Rehearsal
(off-book)
WHO:
Actors, Director, SM, TM, all Designers & Crews
WHAT:
run full show OR cue-to-cue to check all technical elements of the show – identify problems & fix them

## Slide 13: Performance
Perform the show for an audience
WHO:
EVERYONE!!
WHAT:
Perform whole show for and audience

## Slide 14: Post- Production
  Strike
  WHO:
  all actors, designers, crew… EVERYONE!
  WHA Clean-up and put away the show so you are ready for the next production